## Feuille1
Task	Description	Subtask Milestone	Cost %	Cost €	100	← Funds
ActivityPub : go-fed implementation	The go-fed library implements the ActivityPub protocol and the forgefed vocabulary. It is integrated in Gitea to enable the concrete implementation.	pull request(s) to integrate go-fed without inflating the Gitea binary more than 10 %	10,00 %	10,00 €	4,00 €	← Remains
		pull request(s) to allow running the test server on a LAN	5,00 %	5,00 €
				0,00 €
ActivityPub : user private keypairs	A private key is generated for every users. Private keys are needed for signing federating request for HTTP Signatures.	pull request(s) to refactor user settings and use the UserSetting table	10,00 %	10,00 €
		pull request(s) to add the actor API endpoint to obtain its public key to verify HTTP requests	5,00 %	5,00 €
		pull request(s) to implement sending a receiving a signed ActivityStream note	2,00 %	2,00 €
ActivityPub : ActivityStream vocabulary	A minimal subset of the ActivityPub vocabulary allows interoperability with other servers such as Mastodon. A user from a Gitea instance can be followed and will display its activity, either via forgefed or via notes if the vocabulary is lacking.	pull request(s) to implement Outbox	2,00 %	2,00 €
		pull request(s) to implement Inbox	2,00 %	2,00 €
		pull request(s) to implement Follow	2,00 %	2,00 €
		pull request(s) to implement Un-Follow	2,00 %	2,00 €
Forgefed : evolution of the vocabulary	The forgefed vocabulary has not been updated in over a year and never use in real world situation. It needs to be adapted for the need of Gitea.	pull request(s) to adapt Commit	5,00 %	5,00 €
		pull request(s) to adapt Repository	5,00 %	5,00 €
				0,00 €
Link with external data	External users are represented in Gitea and can be linked with a native Gitea user. It is used to keep track of the relationship with user authenticated via, for instance, OAuth2 providers such as a third party forge (Gitea, GitLab, etc.). A similar representation is required to associate a project, an issue, a pull request with its federated counterpart located in another forge.	pull request(s) to add a database representation for external issues	5,00 %	5,00 €
		pull request(s) to add a database representation for external pull requests	5,00 %	5,00 €
		pull request(s) to add a database representation for external project	5,00 %	5,00 €
				0,00 €
				0,00 €
				0,00 €
Converting external references	An issue is referenced from a pull request with a short mention such as #2345 or !5445. These references are relative to the project being federated and must be converted when represented in the context of another federated forge.	pull request(s) to dereference users	4,00 %	4,00 €
		pull request(s) to dereference pull request	4,00 %	4,00 €
		pull request(s) to dereference issues	4,00 %	4,00 €
				0,00 €
				0,00 €
Project data storage	The state of a software project is stored in a git repository, alongside the code, similar to how the wiki data is stored in a .wiki git repository. The state is stored using the Gitea migration file format. It is useful for other federated forges to conveniently get the entire state of the project using git fetch. It can also potentially be used by other forges for the same purpose without requiring complex interactions with the API.	pull request(s) to create a repository to store the project data	2,00 %	2,00 €
		pull request(s) to display the repository in the web User Interface	3,00 %	3,00 €
		pull request(s) to implement a cron job to update the project data repository on a regular basis	2,00 %	2,00 €
				0,00 €
				0,00 €
				0,00 €
				0,00 €
Reporting	Monthly report published on https://blog.gitea.io/ with detailed information about the work done regarding federation since the last report, including links where it can be audited.	February blog post	0,50 %	0,50 €
		March blog post	0,50 %	0,50 €
		April blog post	0,50 %	0,50 €
		May blog post	0,50 %	0,50 €
		June blog post	0,50 %	0,50 €
		July blog post	0,50 %	0,50 €
		August blog post	0,50 %	0,50 €
		September blog post	0,50 %	0,50 €
Videoconferences	Organize a monthly public, online, meeting to discuss the monthly report. The videoconference is open to the general public and recorded.	February recording of the videoconference	0,50 %	0,50 €
		March recording of the videoconference	0,50 %	0,50 €
		April recording of the videoconference	0,50 %	0,50 €
		May recording of the videoconference	0,50 %	0,50 €
		June recording of the videoconference	0,50 %	0,50 €
		July recording of the videoconference	0,50 %	0,50 €
		August recording of the videoconference	0,50 %	0,50 €
		September recording of the videoconference	0,50 %	0,50 €
Diversity	Improving the gender and linguistic diversity is an ongoing challenge for every Free Software project, Gitea included. It must be addressed by concrete actions to improve the situation.	February, March, April blog post summarizing actions to improve diversity	2,00 %	2,00 €
		May, June, July blog post summarizing actions to improve diversity	2,00 %	2,00 €
		August, September blog post summarizing actions to improve diversity	2,00 %	2,00 €